Oʻahu Kūpuna Caregiver Support and Navigation Pilot Program

SCOPE OF WORK

I. INTRODUCTION

The Hawaiʻi State Department of Health (DOH) recognizes that kūpuna caregivers, many of whom shoulder full-time caregiving responsibilities unexpectedly, often face significant challenges accessing and navigating today’s increasingly digital service systems. Limited digital literacy, combined with the emotional, financial, and logistical pressures of caregiving, can make it difficult for caregivers to connect with essential supports, benefits, and resources. In response, the Department acknowledges an urgent need to strengthen caregiver support systems while also improving digital readiness to ensure kūpuna caregivers can more easily engage with modern platforms and services.

The DOH, Maternal and Child Health Branch (MCHB), seeks to implement an Oʻahu-based Kūpuna (grandparents or elders) Caregiver Support and Navigation Pilot Program. This first-year exploratory initiative is designed to assess the feasibility, demand, and system impact of a navigation-focused model supporting kūpuna caregivers raising their moʻopuna (grandchildren) outside of formal child welfare involvement.

For purposes of this solicitation, “kūpuna caregiver” refers to a biological or hānai (traditional practice of informally adopting or raising a child, usually by relatives or close friends) grandparent, older relative, or intergenerational family member serving as the primary caregiver of a related child (birth through age 18), whether through formal or informal arrangements.

Many of these informal ʻohana (family) caregiving arrangements occur outside of the Child Welfare Services (CWS) system. Kūpuna caregivers frequently navigate complex school, healthcare, legal, and public benefit systems without structured support. Strengthening these arrangements and improving system access may promote household stability and reduce preventable involvement with CWS.

Services funded under this solicitation are not intended to duplicate child welfare case management, legal services, home visiting, behavioral health, aging services, or parenting education programs such as Parent Line. The Contractor shall function as an Oʻahu-based navigation and stabilization pilot resource for kūpuna caregivers.

This initiative is designed to:

- Improve identification and connection to existing supports;

- Reduce caregiver isolation;

- Improve access to benefits and services;

- Strengthen caregiver confidence in navigating systems;

- Increasing digital literacy; and,

- Identify recurring barriers impacting informal ʻohana caregiving households.

DOH seeks a qualified organization to deliver navigation-focused support services on Oʻahu during this initial exploratory pilot year.  Year One will prioritize service mapping, utilization analysis, and identification of systemic barriers to inform potential future expansion.

II. SERVICE SPECIFICATIONS

A. Specific Qualifications or Requirements

The Contractor shall demonstrate the capacity to operate an Oʻahu pilot kūpuna caregiver navigation initiative with appropriate administrative and operational rigor. At a minimum, the Contractor shall:

- Demonstrate relevant experience in at least two of the following areas:
a. Supporting kūpuna caregivers or older adults in caregiving roles;
b. Providing family navigation or stabilization services;
c. Operating a referral and systems navigation model; or
d. Serving multigenerational or informal ʻohana caregiving households.

- Demonstrate working knowledge of:
a. Public benefit systems (e.g., DHS General Assistance, SNAP, TANF, Med-QUEST, SSI, WIC);
b. Other support services (e.g., After School Programs, School Meal Programs, Tutoring, Community-Based Programs for Children);
c. Hawaiʻi Department of Education system navigation and school engagement processes;
d. Guardianship and custody referral pathways (non-legal advice); and
e. Barriers commonly experienced by informal ʻohana caregiving households.

- Demonstrate experience operating a navigation-based service model (phone, virtual via an online platform or video conferencing, and/or in-person or hybrid formats) that prioritizes system access and stabilization rather than intensive case management.

- Maintain established administrative systems capable of documenting service contacts, tracking referrals, safeguarding confidential information, and meeting State reporting requirements.

  - Demonstrate fiscal and administrative capacity to manage a contract of approximately $99,808 annually.

  - Demonstrate culturally responsive practices reflective of Hawaiʻi’s communities and respect for informal ʻohana caregiving structures.

Eligible applicants may include nonprofit organizations, community-based organizations, or entities with demonstrated experience in navigation-based service delivery and Oʻahu pilot coordination capacity.  Findings from the pilot year will inform future decisions regarding program continuation, expansion, or modification.

B. DESCRIPTION OF TASKS, RESPONSIBILITIES, AND DELIVERABLES

The services shall prioritize navigation, coordination, and caregiver capacity-building rather than intensive direct service provision. Subcontracting or regional partnerships may be utilized to ensure Oʻahu pilot reach but are not required. The Contractor shall retain responsibility for coordination, oversight, reporting, and fiscal accountability.

Services provided under this contract shall complement, rather than duplicate, services offered through Parent Line, aging services, or other DOH-funded programs.

1. Oʻahu pilot Kūpuna Navigation Access Point

The Contractor shall establish and maintain a single Oʻahu-based navigation access point (phone and email required; virtual/in-person optional based on capacity).  Activities shall include:

a. Intake and basic screening of needs;
b. Identification of appropriate existing services;
c. Warm handoffs to community or government systems; and
d. Follow-up, as appropriate, to confirm connection.

For purposes of this solicitation, “warm handoff” means direct facilitation of connection to another service provider, including real-time phone introduction, electronic referral with follow-up confirmation, or other active engagement to support successful linkage Deliverables shall include:

a. Operational navigation access point within sixty (60) days of contract start;
b. Monthly documentation of inquiries received;
c. An estimated annual target of approximately fifty (50) to seventy-five (75) navigation encounters, recognizing that Year One will establish baseline utilization data;
d. Implementation of a brief user feedback mechanism to inform pilot evaluation;

e. Documentation of warm handoffs completed;

f. Summary of referral outcomes included in monthly reports; and
g. Outreach activities to publicize availability of services.

2. Systems Navigation Support

The Contractor shall provide navigation assistance to kūpuna caregivers related to:

a. Public benefit access (e.g., SNAP, TANF, QUEST, SSI);
b. School enrollment and engagement systems;
c. Legal guardianship referral pathways (non-legal advice);
d. Healthcare and behavioral health referral access; and
e. Youth services and community-based supports.

Deliverables shall include:

a. Documentation of navigation contacts and referral types;
b. Tracking of successful system connections (as reported by caregiver); and
c. Quarterly summary of the most common navigation barriers encountered.

3. Caregiver Connection and Capacity-Building Opportunities

The Contractor shall facilitate a minimum of two (2) structured caregiver connection opportunities annually, which may include workshops, peer connection gatherings, or hybrid formats.

The Contractor shall:

a. Submit an Annual Engagement Plan within sixty (60) days of contract start

outlining proposed topics, format, and projected schedule for DOH review and

approval;
b. Deliver a minimum of two (2) sessions via virtual and/or in-person formats;
c. Maintain an average attendance of approximately twelve (12) to fifteen (15)

kūpuna caregivers per session; and
d. Ensure sessions complement, rather than duplicate, existing community

services.

4. Digital Navigation and Caregiver Capacity Support

The Contractor shall provide individualized digital navigation support to kūpuna caregivers encountering barriers related to technology and online systems.

Activities may include:

a. Assistance with school portals and grade systems;
b. Telehealth access support;
c. Online benefits application navigation;
d. Email setup and document upload assistance;
e. Smartphone use basics including apps and QR codes; and
f. Online safety and fraud awareness education.

Deliverables shall include

a. Documentation of digital navigation encounters; and

b. Integration of building digital literacy and technological skill-building into

workshops and individual navigation contacts.

5. Resource Awareness and Barrier Identification

The Contractor shall maintain awareness of Oʻahu-based resources relevant to kūpuna caregivers and identify recurring system barriers impacting informal ʻohana caregiving households.

Deliverables shall include:

a. One (1) consolidated Pilot Evaluation Summary due within thirty (30) days of contract completion.

6. REPORTING REQUIREMENTS

The Contractor shall submit monthly reports in a format specified by DOH.

Monthly reports shall include:

a. Number of kūpuna caregivers served

b. Number of navigation contacts

c.  Number of warm handoffs completed

d.  Referral categories

Quarterly reports shall include:

a.  Barrier trends

b.  Emerging themes

Final report shall include:

a. Pilot Evaluation Summary

C. PERIOD OF PERFORMANCE

The period of performance shall be March 24, 2026 through March 23, 2027.

III.	Quote Submittal, Payments, and Invoicing Procedures

- Submitting a Quote

Submit a quote following the requirements of the scope of work to provide the requested services for the period March 24, 2026 to March 23, 2027

- The attached Deliverable Cost and Timeline Quote table must be completed and submitted as part of the Bidder’s response to this solicitation. Each task and responsibility listed in Section II, B. Tasks and Responsibilities must be included in the Deliverable Cost and Timeline Quote table. Cost should be based on the administration, purchase and delivery, and evaluation of the project not to exceed $99,808.00.  The quote must include a detailed Narrative clearly describing how the Bidder meets II. Service Specifications: A. Specific Qualifications or Requirements and B. Tasks and Responsibilities. The detailed Narrative shall include the following information: response to service specifications on specific qualifications or requirements, description of the Bidder’s organization in relationship to tasks and responsibilities and compliance with the deliverables in the Cost and Timeline Quote. Additional documentation should be included as attachments to the quote.

- The quote must include a description of the Bidder’s invoicing procedure and a statement of the Bidder’s ability to receive payment in the form of a purchase order.

- Note: Awarded Vendor shall acknowledge that “no work shall be undertaken prior to purchase order approval.” The State of Hawaii is not liable for any work, contracts, costs, loss of profits, or any damages whatsoever incurred by the Awarded Vendor prior to the purchase order approval.

- Form of Payment

Awarded Vendor shall be equipped to accept State purchase order. In addition, Awarded Vendor may be asked to be equipped to accept payment via credit card.

- Procedure for Invoicing

- Awarded Vendor shall submit invoices based upon completion of deliverables.

- No advance payment shall be made.

- The final invoice shall be submitted within thirty (30) days after the end of the project period.

- Payment on the last invoice will not be processed until all tasks as per the Cost and Timeline Quote Table, responsibilities, deliverables, and activities including required reports, is completed to the DOH’s satisfaction.

- Fee to NIC Hawaii

Please be advised that the Awarded Vendor will be responsible to pay NIC Hawaii a fee of 0.75% of the Award, capped at $5,000. NIC will bill the Vendor directly via e-mail and the Vendor can make payment online or by sending a check via regular mail. For technical assistance with HIePRO, please call NIC Hawaiʻi at 808-695-4620.

- Hawaii Compliance Express

State agencies can award amounts of $2,500.00 or greater only to those companies that are registered with Hawaii Compliance Express (HCE). The HCE is an electronic system that allows companies doing business with State or County agencies to quickly and easily obtain proof that they are compliant with applicable laws. The HCE certificate, “Certificate of Vendor Compliance,” is submitted in place of a tax clearance, labor certificate, and a Certificate of Good Standing required in Hawaii Revised Statues (HRS) §103-D-310(c) and Hawaii Administrative Rules (HAR) §3-122-112. For most efficient and timely processing, please register now on Hawaii Compliance Express for a fee of $12 per year at https://vendors.ehawaii.gov/hce/splash/welcome.html. For assistance with HCE registration, please call NIC Hawaii at 808-695-4620.

| Cost and Timeline Proposal Fiscal Year | Tasks and Responsibilities | SUBTOTAL |
| --- | --- | --- |
| Sub Total |  |  |
| Hawaiʻi General Excise Tax |  |  |
| Total |  |  |