PROJECT: HDOT Facility Grouted Rubble Paving Installation
LOCATION: State of Hawaii DOT Highways Division, Materials Testing & Research Branch 2530 Likelike Highway, Honolulu, HI 96819
CLOSING DATE FOR SUBMISSIONS: 06/17/2026
1. PROJECT OVERVIEW
The State of Hawaii / Owner is seeking competitive lump-sum bids from qualified, licensed commercial masonry or civil contractors (License Classification A or C-31 required in the State of Hawaii) to install a grouted rubble paving system on-site at the HDOT Materials Testing & Research Branch.
2. SPECIFIC SITE & OPERATIONAL RESTRAINTS
· Restricted Working Hours: All loud construction, heavy equipment operation, and material deliveries are strictly restricted to off-peak hours: 8:30 AM to 3:00 PM, Monday through Friday.
· Facility Access: The contractor must coordinate crew badging, vehicle access, and staging areas to ensure zero disruption to active HDOT testing bays and facility traffic.
· Traffic Control: The contractor is responsible for providing all necessary cones, signs, or barriers to isolate the work zone safely.

3. SCOPE OF WORK & TECH SPECS
The contractor shall provide all labor, materials, equipment, hauling, and mobilization to complete the following in strict accordance with HDOT Standard Specifications Section 612:
· Excavation & Subgrade: Excavate a 75’ L x 15’ W x 2’ D footprint (83.33 CY). Dispose of all spoils off-site legally. Compact subgrade to 95% AASHTO T-180 and lay Class 1 geotextile filter fabric.
· Material Standards: Supply clean, sound local volcanic basalt stone (minimum 5" thickness). Grout must be a standard 1:3 Portland cement-to-sand mix.
· Testing Allowance: The contractor must cooperate with on-site HDOT technicians who will pull grout test cylinders for compression testing.
· Weep Holes & Finish: Install 3" PVC weep holes spaced 8' on center, staggered. Hand-tool all surface joints to a 1/4-inch recess. Clean all excess grout off rock faces within 24 hours to ensure a clean, natural stone texture. Final surface variance must not exceed 3/8" under a 10-foot straightedge.

4. PROJECT DIMENSIONS
· Total Footprint: 75 Feet x 15 Feet (1,125 Square Feet)
· Thickness: 2 Feet Monolithic
· Total Volume: 83.33 Cubic Yards

5. BID BREAKDOWN REQUIREMENT

Contractor quotes must be submitted as a lump sum broken down by these line items:
1. Site Mobilization, Facility Badging, and Safety Setup: $___________
2. Excavation, Hauling, and Base Prep (including Geotextile): ___________ 
3. Pre-Approved Materials (Basalt Stone, 1:3 Grout Mix, PVC Weep Holes): ___________
4. Craft Labor, Masonry Setup, Tooling, and Curing Management: ___________ 
5. Hawaii GET (4.5%): ___________
TOTAL PROJECT LUMP SUM BID: $___________

6. CONTACT INFORMATION & SITE VISITS
To schedule an on-site inspection or to submit clarifications, contact:
Rennie Serrano
HDOT Highways Division
Materials Testing and Research Branch
[image: Map with pin with solid fill] 2530 Likelike Highway, Honolulu, Hawaii 96819-2928
☏ (808) 832-3405 ext. 103
✉ rennie.b.serrano@hawaii.gov
Structural Notes & Dimensions
· Finished Surface Elevation: Must align flush with adjacent grade or ditch banks to prevent undermining.
· Stone Specification: Clean, sound Hawaii volcanic basalt. No stone shall be less than 5 inches in any dimension.
· Grout Matrix: Monolithic 1:3 Portland cement/sand mix. Voids must be filled 100% with no air pockets.
· Subgrade: Compacted to 95% AASHTO T-180. geotextile filter fabric (Class 1) to be laid beneath the stones if site suffers from severe soil migration.
· Drainage: 3-inch PVC weep holes placed every 8 feet on center, staggered, to relieve hydrostatic pressure behind/underneath the slab.
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