Addendum to Solicitation No. Q18001891
Repair and Resurfacing of Roadway and Parking Lot
Keaiwa Heiau State Recreation Area


1. To all sections, remove language, To make necessary road edge repair to prevent road edge failure.
2. Section 2 – Adding one (1) additional section, total of three (3) sections to be saw cut and repaired.  Replace with 2” layer of asphalt state mix no.5.  Increased square footage from approximately 50 sq. ft. to approximately 120 sq. ft. total.  See attached photo 2b.
3. [bookmark: _GoBack]Section 3 - Provide leveling course to fill in difference in road height. Overlay 2” layer of asphalt state mix no. 5.  Increased square footage from approximately 3,500 sq. ft. to approximately 4,000 sq. ft.
4. Section 4 – Overlay 2” layer of asphalt state mix no.5.
5. Section 6 - Provide leveling course to fill in potholes in the parking lot.  Overlay 2” layer of asphalt state mix no. 5.   
6. Section 7 - Remove and replace entire section with 2” layer of asphalt state mix no.5.  Remove surface roots to provide smooth finish.
7. Section 8 - Provide leveling course to fill in potholes in the roadway.  Overlay 2” layer of asphalt state mix no. 5.  Remove surface roots to provide smooth finish.
8. Section 9 - Provide leveling course to fill in potholes in the roadway.  Overlay 2” layer of asphalt state mix no. 5.  Remove surface roots to provide smooth finish.
9. Section 10 – Remove and replace entire section with 2” layer of asphalt state mix no.5 
Remove surface roots to provide smooth finish.
10. Section 11 - Remove and replace entire section with 2” layer of asphalt state mix no.5 
Remove surface roots to provide smooth finish.  Approximately 300 sq. ft., no square footage was initially given in the solicitation.
11. Section 12 – Apply traffic yellow thermoplastic tape on all speed bumps.  Apply diagonally, 2’ on center.  




